## Project Timeline
Walking Traffic Counter
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2018-01-28 | Got started with timeline and Arduino parts | 20 | 0 | 20 | 2018-01-28 | Got started with timeline and Arduino parts
2018-02-04 | Started UML designs and ordered parts | 8 | 0 | 8 | 2018-02-04 | Started UML designs and ordered parts
2018-02-08 | Class time for Project | -10 | 0 | -10 | 2018-02-08 | Class time for Project
2018-02-11 | Started test cases and configured Github | 15 | 0 | 15 | 2018-02-11 | Started test cases and configured Github
2018-02-18 | Finalized Initial Dia diagrams and test cases | -15 | 0 | -15 | 2018-02-18 | Finalized Initial Dia diagrams and test cases
2018-02-23 | Finalize and Turn in Midway Deliverables | 20 | 0 | 20 | 2018-02-23 | Finalize and Turn in Midway Deliverables
2018-02-24 | Midway Deliverables Due | -5 | 0 | -5 | 2018-02-24 | Midway Deliverables Due
2018-02-25 | Setting up Arduino and calibrating sensors, start Fritzing | 10 | 0 | 10 | 2018-02-25 | Setting up Arduino and calibrating sensors, start Fritzing
2018-03-04 | Setting up the MySQL DB and connecting it to Arduino | -18 | 0 | -18 | 2018-03-04 | Setting up the MySQL DB and connecting it to Arduino
2018-03-10 | Spring Break, work on separate APIs | 18 | 0 | 18 | 2018-03-10 | Spring Break, work on separate APIs
2018-03-18 | Fritzing Diagram, Finalize UML diagrams, and work on test cases | -5 | 0 | -5 | 2018-03-18 | Fritzing Diagram, Finalize UML diagrams, and work on test cases
2018-03-25 | Make sure front end is functional, work on API and documentation |  | 0 | 5 | 2018-03-25 | Make sure front end is functional, work on API and documentation
2018-03-31 | Finish presentation, team evals, and submit project | -17 | 0 | -17 | 2018-03-31 | Finish presentation, team evals, and submit project

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 5 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 17 | 13 | 1 | 2018-01-28 | Got started with timeline and Arduino parts | 20 | 12 | 13 | 2018-01-28 | Got started with timeline and Arduino parts | 20
|  |  | 12 | 2 | 2018-02-04 | Started UML designs and ordered parts | 8 | 11 | 12 | 2018-02-04 | Started UML designs and ordered parts | 8
|  |  | 11 | 3 | 2018-02-08 | Class time for Project | -10 | 10 | 11 | 2018-02-08 | Class time for Project | -10
|  |  | 10 | 4 | 2018-02-11 | Started test cases and configured Github | 15 | 9 | 10 | 2018-02-11 | Started test cases and configured Github | 15
|  |  | 9 | 5 | 2018-02-18 | Finalized Initial Dia diagrams and test cases | -15 | 8 | 9 | 2018-02-18 | Finalized Initial Dia diagrams and test cases | -15
|  |  | 8 | 6 | 2018-02-23 | Finalize and Turn in Midway Deliverables | 20 | 7 | 8 | 2018-02-23 | Finalize and Turn in Midway Deliverables | 20
|  |  | 7 | 7 | 2018-02-24 | Midway Deliverables Due | -5 | 6 | 7 | 2018-02-24 | Midway Deliverables Due | -5
|  |  | 6 | 8 | 2018-02-25 | Setting up Arduino and calibrating sensors, start Fritzing | 10 | 5 | 6 | 2018-02-25 | Setting up Arduino and calibrating sensors, start Fritzing | 10
|  |  | 5 | 9 | 2018-03-04 | Setting up the MySQL DB and connecting it to Arduino | -18 | 4 | 5 | 2018-03-04 | Setting up the MySQL DB and connecting it to Arduino | -18
|  |  | 4 | 10 | 2018-03-10 | Spring Break, work on separate APIs | 18 | 3 | 4 | 2018-03-10 | Spring Break, work on separate APIs | 18
|  |  | 3 | 11 | 2018-03-18 | Fritzing Diagram, Finalize UML diagrams, and work on test cases | -5 | 2 | 3 | 2018-03-18 | Fritzing Diagram, Finalize UML diagrams, and work on test cases | -5
|  |  | 2 | 12 | 2018-03-25 | Make sure front end is functional, work on API and documentation |  | 1 | 2 | 2018-03-25 | Make sure front end is functional, work on API and documentation
|  |  | 1 | 13 | 2018-03-31 | Finish presentation, team evals, and submit project | -17 | 0 | 1 | 2018-03-31 | Finish presentation, team evals, and submit project | -17